## Sheet1
Release No | Publish Type(Web Posting/Manufacturing) | Release Type(Major/Patch/EP/Customer) | RTO Date | Web Posting Date | GA Date | Release Manager | Status | vSphere Version | ​Internal VC | Minimum External ​VC | vSAN Version | Code Base | Brief
3.5 (Ghent) | Manufacturing (Quanta) | Major | 5/27/16 | / | 6/10/16 | Gordon/Sandy | Done | 6.0 U2 | ​6.0 U2 | ​ | vSAN 6.2 |  | Multiple new features. See details in Ghent Release (R3.5)
4(Nicias) |  | Major |  | / |  | Sandy/Shannon | Done | 6.0 P03 | 6.0 U2​ | ​ | vSAN 6.2
4.0.0001 | Web posting | EP |  | 12/16/16 | N/A | Sandy | Done | 6.0 P04 | ​6.0 U2a | ​ | vSAN 6.2 | 4 | To include VMWare ESXi 6.0 P04 which has critical vSAN issue fix.
4.0.100(Nicias+) | Web posting and Manufacturing (Quanta) | Patch |  | 1/20/17 | 2/11/17 (Quanta only) | Xiaofeng | Done | 6.0 P04 | ​6.0 U2a | ​ | vSAN 6.2 | 4.0.0001 | Bug fix and China Branding
4.0.132 | Web posting and Manufacturing (Dell13G) | EP |  | 3/7/17 | 4/18/17 (Dell only) | Xiaofeng/Lynn | Done | 6.0 U3 | ​6.0 U3 | ​ | vSAN 6.2 | 4.0.131 | To include VMWare ESXi 6.0 U3 which has fix for known ESXi and VCSA issue, also includes performance improvements in log management and storage and checksum
4.0.200 | Web posting and Manufacturing (Quanta) | Major |  | 4/26/17 | 5/1/17(Quanta only) | Justin | Done | 6.0 EP07a | ​6.0 U3a | ​ | vSAN 6.2
4.0.300 | Web posting | Major | 6/13/17 | 6/20/17 | N/A | Liyun | Done | 6.0 P05 | ​6.0 U3b | ​ | vSAN 6.2
4.0.301 | Web posting | EP |  | 7/19/17 | N/A | Lynn | Done | 6.0 P05 | ​6.0 U3b | ​ | vSAN 6.2 | 4.0.300 | To fix catastrophic bug in 4.0.300 release: PR 1883468-Cron job collector.sh not deleting the lock file
4.0.302 | Web posting | EP |  | 10/13/17 | N/A | Julia/Lynn | Done | 6.0 EP11 | ​6.0 U3b | ​ | vSAN 6.2 | 4.0.301 | To include VMWare ESXi 6.0 EP11 which has critical vSAN issue fix.
4.0.303 | Web posting | Customer | 10/31/17 | 10/31/17 | N/A | Julia | Done | 6.0 EP11 | ​6.0 U3b | ​ | vSAN 6.2 | 4.0.302 | To address the security issue that VC read-only user can shutdown vxrail.
4.0.310 | Manufacturing (Quanta+Dell 13G) | Major |  | N/A | 9/26/17 (DELL) 10/3/17(Quanta) | Liyun | Done | 6.0 P05 | ​6.0 U3b | ​ | vSAN 6.2 | 4.0.300 | Manufacturing only release, cut into manufacturing for the Quanta and 13G.
4.0.400 | Web posting | Patch | 11/17/17 | 12/4/17 | N/A | Jim | Done | 6.0 P06 | ​6.0 U3c | ​ | vSAN 6.2 | 4.0.310 | New features and corrects multiple known issues
4.0.401 | Web posting | EP | 1/29/18 | 1/29/18(Local upgrade only) 2/2/18(Full) | N/A | Gordon/Lynn | Done | 6.0 P06 | ​6.0 U3d | ​ | vSAN 6.2 | 4.0.400 | Intel security fix and multiple known issues fix.
4.0.402 | Web posting | EP | 3/30/18 | 4/3/18 | N/A | Gordon/Lynn | Done | 6.0 EP13 | 6.0 U3e​ | ​ | vSAN 6.2 | 4.0.401 | To include vSphere EP release 6.0EP13 which addressed Intel microcode fix to complete the resolution of the speculative execution security issues.
4.0.500 | Web posting | Patch | 7/2/18 | 7/16/18 | N/A | Gordon/Chris/Lynn | Done | 6.0 EP14 | ​6.0 U3f | ​6.0 u3f | vSAN 6.2 | 4.0.402 | 1). Integrate 6.0 EP14 which contain security fix; 2). 3 node upgrade; 3). Oracle security fix;**: critical node expansion issue in 4.0.500, recommend all 4.0.500 systems upgrade to 4.0.510
4.0.510 | Web posting and Manufacturing (Quanta) | Patch | 8/6/18 | 8/8/18 | Quanta 9/5/18 | Chris | Done | 6.0 P07 | ​6.0 U3g | ​6.0 u3f | vSAN 6.2 | 4.0.500 | To integrate vsphere 6.0 P07. Scope including:1. New vsphere 6.0 P07; 2.fixed critical node expansion issue; 3. cut into Quanta Manufacturing
4.0.520 | Web posting | EP | 8/27/18 | 8/31/18 (LCM) 9/6/18 (Full) | N/A | Gordon/Chris | Done | 6.0 EP15 | ​6.0 U3h | ​6.0 u3h/6.5 U2c | vSAN 6.2 | 4.0.510 | To include VMware EP release which addressed Intel security fix (L1 Terminal Fault). Scope including:1. New vsphere EP 6.5 EP08;2. Bug 2136533 fix: LCM failure-unmount ISO;3. VMware KB “side channel aware scheduler” workaround on VxRail cluster
4.0.521 | Web posting | EP | 11/5/18 | 11/5/18 | N/A | Lynn/Chris | Done | 6.0 EP18 | ​6.0 U3h | ​6.0 u3h/6.5 U2c | vSAN 6.2 | 4.0.520 | To include VMware EP release which addressed two critical issues:1. SEsparse snapshot issue;2. vSAN dedupe issue
4.0.522 | Web posting | EP | 11/14/18 | 11/14/18 (LCM) 11/20/18 (Full) | N/A | Lynn/Chris | Done | 6.0 EP19 | ​6.0 U3h | ​6.0 u3h/6.5 U2c | vSAN 6.2 | 4.0.521 | To include VMware EP release containing important security fixes.
​4.0.523 | ​Web Posting | ​EP | 4/2/19​ | ​4/4/19(LCM) 4/18/19(Full) | ​N/A | ​Jason Xu | ​Done | ​6.0 EP20 | ​6.0 U3h | 6.0 U3h/6.5 U2c | ​vSAN 6.2 | ​4.0.522 | ​To sim-ship with VMWare 6.0 EP20 which includes security fixes.
​4.0.524 | ​Web Posting | ​EP | 5/27/19 | ​​5/30/19 (LCM) 6/13/19 (Full) | ​N/A | ​Jason Xu | ​Done | ​6.0 EP21 | ​ | ​6.0 U3i/6.5 U2g/6.7 U2a | ​vSAN 6.2 | ​4.0.522 | ​To simship with VMware 6.0 EP21 which includes security fixes.
4.5 (Tarascon) | Web posting and Manufacturing (Quanta+Dell 13G) | Major | 9/18/17 | 9/29/17 | 11/7/17 (QNTA and DELL) | Shannon (Primary)/Gordon | Done | 6.5 U1 | ​6.5 U1 | ​6.5 U1 | vSAN 6.6.1
4.5.070 | Web posting and Manufacturing (Quanta+Dell 13G) | EP | 10/18/17 | 10/18/17 | Dell 11/22/17 Quanta 12/15/17 | Julia/Lynn | Done | 6.5 EP04 | ​6.5 U1a | ​6.5 U1 | vSAN 6.6.1 | 4.5 | To include VMware EP release 6.5EP04 which includes critical vSAN fixes that correct security and data unavailability issues for all-flash appliances with deduplication enabled.
​4.5.150 | ​Web posting | ​Patch | ​1/29/18 | ​1/29/18(Local Upgrade only) 2/2/18 (Full release) | ​N/A | ​Gordon/Lynn | ​Done | ​6.5P02 | ​6.5 U1e | ​6.5 U1 | ​vSAN 6.6 | ​4.5.070, rebases 4.5.100 | ​Patch release for new features and quality improvements, scope including:1). Mixed node support; 2). Upgrade from 4.0.x to 4.5.150; 3) Role-based control; 4) Intel security fix; 5) Multiple known issue fix(eg: PSU/disk false-positive event report)
4.5.101(Portsmouth/VxRack Lyon ) | Manufacturing (Dell 14G) | Major | 11/21/17 | N/A | 12/29/17 | Xiaofeng(Primary)/Justin | Done | 6.5 EP04 | ​6.5 U1a | ​​6.5 U1 | vSAN 6.6.1 | 4.5 | Manufacturing only - No upgrades supported
4.5.152 | Web posting | EP | 3/30/18 | 4/3/18 | N/A | Gordon/Lynn | Done | 6.5 EP6 | ​6.5 U1g | ​6.5 U1 | vSAN 6.6 | 4.5.150 | To include vSPhere EP release 6.5EP6 which addressed Intel microcode fix to complete the resolution of the speculative execution security issues, also have multiple known issue fixed.
4.5.200 | Manufacturing (Dell 13G+Dell 14G+Quanta) | Major | 2/14/18 | 4/9/18 | 4/17/18 (Dell 13G/14G/Quanta) 7/20/18 C6420/G560 | Justin/Adeline | Done | 6.5 P02 | ​6.5 EP5 | ​​6.5 U1 | vSAN 6.6 |  | Manufacturing only - No upgrades supported. Note that C6420/G560 cut into manufacturing 7/20/18 with 4.5.200.
4.5.210(Munich) | Web posting | Patch | 5/3/18 | 5/10/18 | N/A | Shannon/Chris/Lynn | Done | 6.5 U2 | ​​6.5 U2 | ​6.5 U2 | vSAN 6.6.1 U2 | 4.5.200 | Munich release T2, To support upgrade feature for Munich. Scope including:1). NIC FW LCM;2). Embedded LCM Engine;3). Intel security fix;4). 3 node upgrade
​4.5.211 | ​Web posting | ​EP | ​ | ​6/7/18 | ​N/A | ​Gordon/Lynn | ​Done | ​6.5U2 | ​​6.5 U2 | ​​6.5 U2 | ​vSAN 6.6.1 U2 | ​4.5.210 | ​To fix stretch cluster upgrade issue. Also fixed multiple critical known issues and included new HBA330 driver/FW.
4.5.212 | Web posting | EP | 7/2/18 | 7/10/18 | N/A | Gordon/Lynn | Done | 6.5 EP07 | ​​6.5 U2b | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.211 | To include vSphere EP release 6.5EP07 which addressed Intel security fix,. Also contains Oracle security fix.
4.5.215 | Manufacturing (Quanta+Dell 14G) | Patch | 7/2/18 | 8/28/18 | 8/28/18 (Quanta and Dell 14G) | Chris/Lynn | Done | 6.5 EP07 | ​​6.5 U2b | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.210 | No upgrades supported:1. Introduce Corporate Dell EULA in the VxRail software;2. Quality improvements and new features. 3. Cut into manufacture for VxRail. And to support VxRack manufacture.
4.5.218 | Web posting | EP | 8/27/18 | 8/28/18 (LCM) 9/5/18 (Full) | N/A | Gordon/Chris | Done | 6.5 EP08 | ​​6.5 U2c | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.215 | To include VMware EP release 6.5EP08 which addressed Intel security fix (L1 Terminal Fault). Also includes Broadcom NIC FW in HW LCM and bug fix.
4.5.219 | NA | Customer | 9/12/18 | 9/12/18 | N/A | Charlie | Done | 6.5 EP08 | ​​6.5 U2c | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.215 | Customer releases for Investec only . Scope including:1. LCM maintenance mode enhancement – a) Shorten the MM window, b) Resync awareness. 2. LCM email notification. 3. Bug fix for LCM failure-unmount ISO issue
4.5.225 | Web posting | EP | 10/3/18 | 10/3/18 |  | Chris/Jason | Done | 6.5 EP09 | ​6.5 U2c | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.218 | 1. include VMWare ESXi 6.5 EP09 which has critical vSAN issue ; 2. Include new NIC FW to fix 13G x520Error! Filename not specified. HW LCM issue.3. Include Dell iDRAC 3.21.23.22
4.5.226 | NA | Customer | 10/3/18 | 10/3/18 | N/A | Charlie | Done | 6.5 EP09 | ​6.5 U2c | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.219 | Customer release for Investec only, replace 4.5.219 for NIC HW LCM issue fix, Scope including:1. LCM maintenance mode enhancement – a) Shorten the MM window, b) Resync awareness;2. LCM email notification;3. Bug fix for LCM failure-unmount ISO issue
4.5.227 | Web posting | EP | 11/5/18 | 11/5/18 |  | Chris/Lynn | Done | 6.5 EP10 | ​6.5 U2c | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.225 | To include VMware EP release which addressed two critical issues:1. SEsparse snapshot issue;2. vSAN dedupe issue
4.5.228 | Customer | Customer | 11/5/18 | 11/5/18 |  | Charlie | Done | 6.5 EP10 | ​6.5 U2c | ​​6.5 U2 | vSAN 6.6.1 U2 | 4.5.226 | To include VMware EP release which addressed two critical issues:1. SEsparse snapshot issue;2. vSAN dedupe issue
4.5.229 | Web posting | EP | 11/14/18 | 11/14/18 (LCM) 11/20/18 (Full) | N/A | Lynn/Chris | In Progess | 6.5 EP11 | ​6.0 U3h | ​6.0 u3h/6.5 U2c | vSAN 6.6.1 U2 | 4.5.227 | To include VMware EP release containing important security fixes.
4.5.231 | Customer | EP | 11/14/18 | 11/?/18 | N/A | Charlie | In Progress | 6.5 EP11 | ​6.0 U3h | ​6.0 u3h/6.5 U2c | vSAN 6.6.1 U2 | 4.5.228 | To include VMware EP release containing important security fixes.
4.5.300 | Manufacturing (Dell 14G) and Web posting | Major | 12/3/18 | 12/18/18 (LCM) 1/28/19 (Full) | 3/5/19 | Adeline/Lynn | Completed | 6.5 P03 | 6.5 Update 2d | ​​ | 6.6.1 Patch 03 |  | Cancel MFG due to critical HBA 330 issue.
​4.5.310 | ​Manufacturing (Dell 14G) and Web posting | ​Patch | ​3/15/19 | ​3/18/19 (LCM) 3/27/19 (Full) | ​5/7/19 | Chris/Jason/Lynn​ | ​Completed | ​6.5 P03 | ​6.5 Update 2d |  | ​6.6.1 Patch 03 | ​4.5.300 | ​Critical defect fixing.
​4.5.311 | ​Web posting | ​EP | 4/1/19​ | ​4/3/19(LCM) 4/18/19(Full) | N/A​ | ​Jason Xu | ​Completed | ​6.5EP13 | ​​​6.5 Update 2d |  | ​vSAN 6.6.1 Express Patch 13 | ​4.5.310 | ​To sim-ship with VMWare 6.5 EP13 which includes security fixes.
​4.5.314 | ​Web posting | ​EP | ​5/27/19 | ​5/30/19 (LCM) 6/13/19 (Full) | ​N/A | ​Jason Xu | ​Completed | ​6.5 EP14 | ​6.5 U2g | ​ | ​vSAN 6.6.1 EP14 | ​4.5.311 | ​To simship with VMware 6.5 EP14 which includes security fixes.
​4.5.400 | ​Manufacturing (Dell Intel MLK and web posting) | ​Minor | ​7/8/19 | ​7/16/19 (LCM) 7/31/19 (RASR) | ​8/20/19 | Chris | RTW done | ​6.5 U3 | ​​6.5 U3 | ​​ | vSAN ​​6.5 U3 | ​4.5.300 | ​
4.7.000(Turin) | Manufacturing (Dell 14G) and Web posting | Major | 10/8/18 | 11/16/18 | 12/18/18 | Adeline/Brian | Completed | 6.7 U1 | ​6.7 U1 | ​6.7 U1 | vSAN 6.7 U1
​4.7.001 | ​Web posting | ​ | ​12/4/18 | 12/6/18​ | ​N/A | ​Chris/Jing | Completed | ​6.7 EP5 | 6.7 EP5​ | 6.7 EP5​ | ​vSAN 6.7 U1 | ​4.7.000 | ​Defect fixing.
4.7.100(Abuja) | Manufacturing (Dell 14G) and Web posting | Major | 1/18/19 | 1/22/19 (LCM) 1/28 (Full) | 3/5/19 | Xiaofeng/Brian | Completed | 6.7 EP6 | 6.7 U1b | ​ | vSAN 6.7 EP6 | 4.7.001 | Cancel MFG due to HBA issue.
​4.7.110 | ​Manufacturing (Dell 14G) and Web posting | ​Patch | ​3/15/19 | ​3/18/19 (LCM) 3/27/19 (Full) | 5/7/19​ | ​Chris/Jason/Lynn​ | ​Completed | ​6.7 EP6 | ​6.7 U1b |  | ​vSAN 6.7 EP6 | ​4.7.100 | ​Critical defect fixing. Critical HBA330 issue.
​4.7.111 | ​Web posting | ​EP | ​4/2/19 | ​4/4/19(LCM) 4/18/19(Full) | ​N/A | ​Jason Xu | ​Completed | ​6.7 EP7 | ​6.7 U1b | ​ | ​vSAN 6.7 Express Patch 07 | ​4.7.110 | ​To sim-ship with VMWare 6.7 EP7 which includes security fixes.
​4.7.115 | ​FTP to Kohl's | ​Customer | ​4/29/19 | ​N/A | ​​N/A | ​Jason Xu | ​Completed | ​6.7EP7 | 6.7 U1b | ​ | ​vSAN 6.7 EP7 | ​4.7.111 | ​Provided only to Kohl's to address VC-plugin timeout issue during LCM
​4.7.150(Bishkek) | ​​Manufacturing (Dell 14G AMD) | ​Major | ​​4/2/19 | NA | ​6/25/19 | ​​Adeline/Justin | ​RTOed | ​​​6.7EP7 | ​​6.7 U1b | ​​ | ​​vSAN 6.7 U1 | ​ | ​No RTS due to performance issues.
​4.7.200(MLK) | ​Manufacturing (Dell Intel MLK and Web Posting) | ​Minor | ​4/22/19 5/2/19 | ​5/8/19 (LCM) 5/23/19(RASR) | ​6/18/19 | ​Julia/Justin | ​In progress | ​6.7 U2 | ​6.7 U2 | ​ | ​vSAN 6.7 U2 | ​4.7.100 | ​vSphere 6.7 U2 simship.Critical BIOS issue caused re-spin with BIOS 1.6.11/12 and pull support for Intel MLK. No June block RTS. Pulled for customer upgrades on 5/17/19 due to critical 25G FW issue and BOSS FW update issue. Pulled for support upgrades upon RTW 4.7.211 6/6/19.
​4.7.210 | ​Manufacturing only (MLK) | ​ | ​5/31/19 | N/A | ​​7/16/19 | ​ | ​In progress | ​6.7 EP9 | ​6.7 U2a | ​ | ​vSAN 6.7 EP9 | ​4.7.200 | ​
​4.7.211 | ​Web posting | ​ | 6/4/19​ | ​6/6/19 (LCM) 6/20 (Full) | ​N/A | ​ | ​Completed | ​6.7 EP9 | ​6.7 U2a | ​ | ​vSAN 6.7 EP9 | ​4.7.200 | ​Fixed 2 upgrade related bugs in 4.7.210.
​4.7.300(Shaoxing) | ​Manufacturing (Dell Intel) | ​Major | ​8/19/19 | ​9/10/19 | ​10/15/19 | ​Michael/Brian | ​In Progress | ​6.7 U3 | ​6.7 U3 | ​6.7 U3 | ​vSAN 6.7 U3 | ​4.7.100 | ​Shaoxing will run Intel based platforms only

## Sheet2
Release No | RTO Date | Web Posting Date | GA Date | Date
3.5 (Ghent) | 5/27/16 | / | 6/10/16 | 2016-10-06
4.0.0001 |  | 12/16/16 | N/A | 2016-12-16
4.0.100(Nicias+) |  | 1/20/17 | 2/11/17 (Quanta only) | 2017-02-11
4.0.132 |  | 3/7/17 | 4/18/17 (Dell only) | 2017-04-18
4.0.200 |  | 4/26/17 | 5/1/17(Quanta only) | 2017-05-01
4.0.300 | 6/13/17 | 6/20/17 | N/A | 2017-06-20
4.0.301 |  | 7/19/17 | N/A | 2017-07-19
4.0.302 |  | 10/13/17 | N/A | 2017-10-13
4.0.303 | 10/31/17 | 10/31/17 | N/A | 2017-10-31
4.0.310 |  | N/A | 9/26/17 (DELL) 10/3/17(Quanta) | 2017-10-03
4.0.400 | 11/17/17 | 12/4/17 | N/A | 2017-12-04
4.0.401 | 1/29/18 | 1/29/18(Local upgrade only) 2/2/18(Full) | N/A | 2018-02-02
4.0.402 | 3/30/18 | 4/3/18 | N/A | 2018-04-03
4.0.500 | 7/2/18 | 7/16/18 | N/A | 2018-07-16
4.0.510 | 8/6/18 | 8/8/18 | Quanta 9/5/18 | 2018-08-08
4.0.520 | 8/27/18 | 8/31/18 (LCM) 9/6/18 (Full) | N/A | 2018-09-06
4.0.521 | 11/5/18 | 11/5/18 | N/A | 2018-11-05
4.0.522 | 11/14/18 | 11/14/18 (LCM) 11/20/18 (Full) | N/A | 2018-11-20
​4.0.523 | 4/2/19​ | ​4/4/19(LCM) 4/18/19(Full) | ​N/A | 2019-04-18
​4.0.524 | 5/27/19 | ​​5/30/19 (LCM) 6/13/19 (Full) | ​N/A | 2019-05-30
4.5 (Tarascon) | 9/18/17 | 9/29/17 | 11/7/17 (QNTA and DELL) | 2017-11-07
4.5.070 | 10/18/17 | 10/18/17 | Dell 11/22/17 Quanta 12/15/17 | 2017-12-15
​4.5.150 | ​1/29/18 | ​1/29/18(Local Upgrade only) 2/2/18 (Full release) | ​N/A | 2018-02-02
4.5.101(Portsmouth/VxRack Lyon ) | 11/21/17 | N/A | 12/29/17 | 2017-12-29
4.5.152 | 3/30/18 | 4/3/18 | N/A | 2018-04-03
4.5.200 | 2/14/18 | 4/9/18 | 4/17/18 (Dell 13G/14G/Quanta) 7/20/18 C6420/G560 | 2018-07-20
4.5.210(Munich) | 5/3/18 | 5/10/18 | N/A | 2018-05-10
​4.5.211 | ​ | ​6/7/18 | ​N/A | 2018-06-07
4.5.212 | 7/2/18 | 7/10/18 | N/A | 2018-07-10
4.5.215 | 7/2/18 | 8/28/18 | 8/28/18 (Quanta and Dell 14G) | 2018-08-28
4.5.218 | 8/27/18 | 8/28/18 (LCM) 9/5/18 (Full) | N/A | 2018-09-05
4.5.219 | 9/12/18 | 9/12/18 | N/A | 2018-09-12
4.5.225 | 10/3/18 | 10/3/18 |  | 2018-10-03
4.5.226 | 10/3/18 | 10/3/18 | N/A | 2018-10-03
4.5.227 | 11/5/18 | 11/5/18 |  | 2018-11-05
4.5.228 | 11/5/18 | 11/5/18 |  | 2018-11-05
4.5.229 | 11/14/18 | 11/14/18 (LCM) 11/20/18 (Full) | N/A | 2018-11-20
4.5.231 | 11/14/18 | 11/?/18 | N/A | 2018-11-14
4.5.300 | 12/3/18 | 12/18/18 (LCM) 1/28/19 (Full) | 3/5/19 | 2019-03-05
​4.5.310 | ​3/15/19 | ​3/18/19 (LCM) 3/27/19 (Full) | ​5/7/19 | 2019-05-07
​4.5.311 | 4/1/19​ | ​4/3/19(LCM) 4/18/19(Full) | N/A​ | 2019-04-18
​4.5.314 | ​5/27/19 | ​5/30/19 (LCM) 6/13/19 (Full) | ​N/A | 2019-06-13
​4.5.400 | ​7/8/19 | ​7/16/19 (LCM) 7/31/19 (RASR) | ​8/20/19 | 2019-08-20
4.7.000(Turin) | 10/8/18 | 11/16/18 | 12/18/18 | 2018-11-16
​4.7.001 | ​12/4/18 | 12/6/18​ | ​N/A | 2018-12-06
4.7.100(Abuja) | 1/18/19 | 1/22/19 (LCM) 1/28 (Full) | 3/5/19 | 2019-01-28
​4.7.110 | ​3/15/19 | ​3/18/19 (LCM) 3/27/19 (Full) | 5/7/19​ | 2019-03-27
​4.7.111 | ​4/2/19 | ​4/4/19(LCM) 4/18/19(Full) | ​N/A | 2019-04-18
​4.7.115 | ​4/29/19 | ​N/A | ​​N/A | 2019-04-29
​4.7.150(Bishkek) | ​​4/2/19 | NA | ​6/25/19 | 2019-06-25
​4.7.200(MLK) | ​4/22/19 5/2/19 | ​5/8/19 (LCM) 5/23/19(RASR) | ​6/18/19 | 2019-05-23
​4.7.210 | ​5/31/19 | N/A | ​​7/16/19 | 2019-07-16
​4.7.211 | 6/4/19​ | ​6/6/19 (LCM) 6/20 (Full) | ​N/A | 2019-06-06
​4.7.300(Shaoxing) | ​8/19/19 | ​9/10/19 | ​10/15/19 | 2019-09-10